## Sheet1
Task Name | Layer/Task dependencies | Start Date | End Date | Assigned To | Status
Plan |  | 2018-07-19 | 2018-07-25 | N/A
1 Research algorithm and program structure | 1 | 2018-07-19 | 2018-07-20 | Engineer 1,2,3,4,5 |  | Not Started
2 Create work breakdown structure | 1 | 2018-07-20 | 2018-07-21 | Engineer 1,5 |  | In Progress
3 Plan the implementation/data structures/interfaces | 2 | 2018-07-21 | 2018-07-25 | Engineer 1,2,3,4 |  | Completed
4 Divide tasks, create Gantt chart | 2 | 2018-07-21 | 2018-07-25 | Engineer 1,2,3,4
5 Plan animation states and flow graphs | 2 | 2018-07-21 | 2018-07-25 | Engineer 2,3,4,5
Implementation |  | 2018-07-25 | 2018-08-12 | N/A
6 Input parsing | 3 | 2018-07-25 | 2018-07-27 | Edwar
7 Output construction | 3 | 2018-07-25 | 2018-07-27 | Edwar
8 BBA* recursion | 3 | 2018-07-25 | 2018-08-02 | Alex
9 Pre-processing | 3 | 2018-07-25 | 2018-08-04 | Engineer 4
10 Post-processing | 3 | 2018-07-25 | 2018-08-04 | Engineer 5
11 I/O data structure/functions (acyclic task graph) | 3 | 2018-07-25 | 2018-08-04 | Engineer 1
12 Implement animations | 3 | 2018-07-25 | 2018-08-10 | Cameron
13 BBA* data structure/functions | 3 | 2018-07-25 | 2018-08-02 | Engineer 3
14 BBA* cost function | 3 | 2018-07-25 | 2018-08-02 | Andrew
Testing |  | 2018-08-10 | 2018-08-18 | N/A
15 Optimality verification | 4 | 2018-08-10 | 2018-08-15 | Andrew
16 Integration testing | 4 | 2018-08-10 | 2018-08-15 | Engineer 5
17 Environment testing | 5 | 2018-08-15 | 2018-08-18 | Engineer 2
18 Efficiency/speed testing | 5 | 2018-08-15 | 2018-08-18 | Engineer 3
Presenting |  | 2018-08-18 | 2018-08-23 | N/A
19 Write conclusion | 6 | 2018-08-18 | 2018-08-21 | Engineer 1,2,3,4,5
20 Write/practice presentation | 6 | 2018-08-18 | 2018-08-23 | Engineer 1,2,3,4,5
21 Write executive summary | 6 | 2018-08-18 | 2018-08-21 | Engineer 1,2,3,4,5
22 Write up results | 6 | 2018-08-18 | 2018-08-21 | Engineer 1,2,3,4,5
23 Create diagrams | 6 | 2018-08-18 | 2018-08-21 | Engineer 1,2,3,4,5
24 Create a wiki | 3 | 2018-07-25 | 2018-07-25 | Engineer 1,2,3,4,5
25 Update wiki | 4 | 2018-08-10 | 2018-08-12 | Engineer 1,2,3,4,5
26 Combine and review report | 7 | 2018-08-23 | 2018-08-23 | Engineer 1,2,3,4,5